## Slide 1: Contract Administration and Claims Procedures for Design Professionals
Prof. Carl Circo, Ben J. Altheimer Professor of Legal Advocacy

## Slide 2: Topics covered
Common tasks that design professionals and construction managers perform during the contract administration period.
Contract administration under the standard AIA approach for the design-bid-build delivery system.
Alternative procedures for informally resolving common claims that arise during construction.
Potential liability risks that contract administration creates for design professionals and construction managers.

## Slide 3: What is contract administration?
“Contract administration” usually refers to a wide range of activities that assist the owner in its contractual relationship with the general contractor, such as:
  providing information to the contractor.
  inspecting the progress of construction.
  preparing documents in connection with changes to the work.
  authorizing payments to the contractor.
  informally helping to resolve claims between the owner and the contractor.
AIA A201 (General Conditions) provides for contract administration as commonly provided by O’s design professional.

## Slide 4: AIA general conditions approach Article 4
Article 4—Administration of the contract.
  A represents O for contract administration purposes.
  Periodic site visits.
  Conduit for O-C communications.
  Review and approval of submittals.
  Responds to requests for information & interprets contract documents.
  Discretion on matters relating to aesthetics.

## Slide 5: AIA general conditions approach Article 7
Article 7—Administration relating to changes.
  A prepares change orders and construction change directives.
  For construction change directives, if necessary, A determines adjustment to contract sum.
  A has authority to order minor changes.

## Slide 6: AIA general conditions approach Article 9
Article 9—Administration relating to payments and completion.
  A reviews C’s schedule of values.
  A reviews C’s applications for progress payments & issues certificates for payment.
  A has authority to withhold payments as O’s representative.
  A determines dates of substantial completion and final completion based on inspections.

## Slide 7: AIA general conditions approach Section 14 and 15
Section 14.2—termination of contractor for cause.
  The Initial Decision Maker (often A) certifies that sufficient cause exists to justify terminating C for cause.
Section 15.1—Any claim by either O or C must be submitted to the Initial Decision Maker.
Section 15.2—Claims are decided by the Initial Decision Maker.
  Initial Decision Maker investigates and issues a decision on the claim if possible.
  The decision is subject to mediation or more formal dispute resolution procedures at either party’s request.

## Slide 8: Contract administration varies with the delivery system
The project design professional commonly provides contract administration for the owner in design-bid-build system or in construction manager at risk system.
EJCDC document C-700 (engineering organizations’ general conditions form) gives the project engineer a contract administration role similar to the architect’s under A201.
A construction manager as agent may take over or share contract administration responsibilities that a design professional performs in design-bid-build.
In public contracts, the owner’s contracting officer often functions as the contract administrator.
There may be no independent contract administration role under a design-build delivery system.
Alternatives to the AIA approach for informal claims management include an independent project neutral or a dispute resolution board.
Contract administration is a matter of negotiation. There are no hard and fast rules, especially when the parties use a delivery system other than design-bid-build.

## Slide 9: Contract administration as professional service
Most contract administration services by a construction industry professional are professional services.
  In relation to O, these services must be provided in accordance with the applicable professional standard of care (architect, engineer, construction manager).
  Other potential liability (e.g., to third parties) based on contract administrative services will be determined under these principles (which are beyond the scope of this presentation):
    Agency law principles may apply to certain services (e.g., approvals).
    Quasi-judicial immunity may apply to certain services (e.g., claims decisions).
    Certification or recommendation to terminate C carries relatively high risk of liability (especially for tortious interference with contract).

## Slide 10: Summary
Owners who lack sufficient construction experience often need a design professional or construction manager to provide contract administration services.
Contract administration services vary depending on the project delivery system being used.
Contract administration services provided by professionals are generally subject to a professional duty of care.
The details of contract administration are negotiable as a matter of contract.